## Launch To-Do Tracker
QUIVIRA AI COURSE — Launch To-Do Tracker ¦ 30-Day Window ¦ April 3 – May 2, 2026
Task | Category | Owner | Due Date | Day # | Priority | Status | Risk Flag | Risk / Fix Suggestion
Write lesson scripts for AI Automation — Beginner Track (M1–M5) | Course Creation | @big_quiv | Apr 12, 2026 | 10 | HIGH | To Do | OK
Write lesson scripts for AI Automation — Developer Track (M1–M6) | Course Creation | @big_quiv | Apr 14, 2026 | 12 | HIGH | To Do | OK
Write lesson scripts for AI Automation — Creator Track (M1–M5) | Course Creation | @big_quiv | Apr 14, 2026 | 12 | HIGH | To Do | OK
Write lesson scripts for AI Automation — Business Track (M1–M5) | Course Creation | @big_quiv | Apr 16, 2026 | 14 | HIGH | To Do | OK
Write lesson scripts for AI Video Creation — all 4 tracks | Course Creation | @big_quiv | Apr 18, 2026 | 16 | HIGH | To Do | ⚠ YES | RISK: 12 tracks of scripts in 16 days is aggressive. Prioritise Beginner + Creator tracks first — they have the largest audience. Defer Developer + Business scripts to Day 18 max.
Write lesson scripts for Coding with AI — all 4 tracks | Course Creation | @big_quiv | Apr 20, 2026 | 18 | HIGH | To Do | ⚠ YES | RISK: Same risk as above. Batch-write with Claude using module outlines as prompts. Target: 2 tracks/day working session.
Create slide decks / visual aids for live sessions (Google Slides) | Course Creation | @big_quiv | Apr 22, 2026 | 20 | MEDIUM | To Do | OK
Record all pre-recorded modules (M2, M5 across topics) | Course Creation | @big_quiv | Apr 26, 2026 | 24 | HIGH | To Do | ⚠ YES | RISK: Pre-recorded modules need to be done by Day 24 minimum to release 48hrs before live sessions. Use screen recording + MiniMax voiceover for efficiency.
Create resource PDFs: prompt templates, workflow checklists, tool guides | Course Creation | @big_quiv | Apr 24, 2026 | 22 | MEDIUM | To Do | OK
Create completion certificate template (branded PDF) | Course Creation | @big_quiv | Apr 28, 2026 | 26 | LOW | To Do | OK
Build Notion portal page (course hub — links to all pre-recorded modules) | Course Creation | @big_quiv | Apr 17, 2026 | 15 | HIGH | To Do | OK
Set up Gumroad products: 3 tiers ($15 / $30 / $50) | Tech Setup | @big_quiv | Apr 15, 2026 | 13 | HIGH | To Do | OK
Set up Selar.co products (Nigerian Naira buyers) | Tech Setup | @big_quiv | Apr 16, 2026 | 14 | MEDIUM | To Do | OK
Create Telegram group for course community (separate from signal group) | Tech Setup | @big_quiv | Apr 10, 2026 | 8 | HIGH | To Do | OK
Set up Google Meet recurring links for live sessions (Tue + Thu evenings) | Tech Setup | @big_quiv | Apr 12, 2026 | 10 | HIGH | To Do | OK
Configure Notion portal with password protection and module links | Tech Setup | @big_quiv | Apr 18, 2026 | 16 | HIGH | To Do | OK
Set up welcome message and onboarding flow in Telegram group | Tech Setup | @big_quiv | Apr 19, 2026 | 17 | MEDIUM | To Do | OK
Test full student journey: payment → Notion access → Telegram invite → first module | Tech Setup | @big_quiv | Apr 22, 2026 | 20 | HIGH | To Do | ⚠ YES | RISK: If this breaks on launch day, students lose confidence immediately. Run a complete dry-run by Day 20 minimum.
Create landing page or Linktree with course links (Gumroad + Selar) | Tech Setup | @big_quiv | Apr 18, 2026 | 16 | MEDIUM | To Do | OK
Set up auto-DM or ManyChat flow for keyword triggers (COURSE, STARTER, BUILDER, FULLACCESS) | Tech Setup | @big_quiv | Apr 20, 2026 | 18 | MEDIUM | To Do | OK
Record Day 1 validation poll content (all 4 platforms) | Content Creation | @big_quiv | Apr 17, 2026 | 15 | HIGH | To Do | OK
Write and schedule Week 1 content (Days 2–7) on Typefully | Content Creation | @big_quiv | Apr 07, 2026 | 5 | HIGH | To Do | ⚠ YES | RISK: Days 2-7 need to be written and scheduled by Day 5. Already have outlines. Execute now.
Write and schedule Week 2 content (Days 8–14) | Content Creation | @big_quiv | Apr 13, 2026 | 11 | HIGH | To Do | OK
Write Weekly Series EP1 (Claude trade journal analysis) | Content Creation | @big_quiv | Apr 11, 2026 | 9 | HIGH | To Do | OK
Write Weekly Series EP2 (Kling AI video workflow) | Content Creation | @big_quiv | Apr 21, 2026 | 19 | HIGH | To Do | OK
Write Weekly Series EP3 (Supabase + Claude + freebie) | Content Creation | @big_quiv | Apr 26, 2026 | 24 | HIGH | To Do | OK
Write Weekly Series EP4 (Remotion batch video generation) | Content Creation | @big_quiv | May 02, 2026 | 30 | HIGH | To Do | OK
Create AI Tool Stack resource PDF (freebie for Day 13) | Content Creation | @big_quiv | Apr 14, 2026 | 12 | MEDIUM | To Do | OK
Write course announcement thread and all platform versions | Content Creation | @big_quiv | Apr 19, 2026 | 17 | HIGH | To Do | OK
Write money proof content — income breakdown thread + carousel | Content Creation | @big_quiv | Apr 18, 2026 | 16 | HIGH | To Do | OK
Create carousel: "What $30 gets you in Quivira AI Course" | Content Creation | @big_quiv | Apr 23, 2026 | 21 | MEDIUM | To Do | OK
Write Week 4 promotional content (Days 22–28) | Content Creation | @big_quiv | Apr 23, 2026 | 21 | HIGH | To Do | OK
Write final push content (Days 29–30) | Content Creation | @big_quiv | Apr 30, 2026 | 28 | HIGH | To Do | OK
Post validation poll on all platforms (Day 15) | Promotion | @big_quiv | Apr 17, 2026 | 15 | HIGH | To Do | OK
Monitor validation poll replies and DM everyone who responds | Promotion | @big_quiv | Apr 18, 2026 | 16 | HIGH | To Do | OK
Drop free Module 1 on Telegram + X (Day 24) | Promotion | @big_quiv | Apr 26, 2026 | 24 | MEDIUM | To Do | OK
Reach out to 5 relevant creators for collaboration / cross-promotion | Promotion | @big_quiv | Apr 22, 2026 | 20 | MEDIUM | To Do | ⚠ YES | RISK: Organic only — this may not yield results in time. Start outreach by Day 12 minimum to allow response time.
Pin course announcement in Telegram group | Promotion | @big_quiv | Apr 19, 2026 | 17 | HIGH | To Do | OK
DM follow-up to everyone who engaged with validation poll | Promotion | @big_quiv | Apr 20, 2026 | 18 | HIGH | To Do | OK
Create urgency posts for Days 27–29 (3-day countdown) | Promotion | @big_quiv | Apr 28, 2026 | 26 | HIGH | To Do | OK
Collect student testimonials from Week 1 and publish as social proof | Promotion | @big_quiv | Apr 27, 2026 | 25 | MEDIUM | To Do | OK
Write Telegram welcome message for course community | Community Setup | @big_quiv | Apr 10, 2026 | 8 | HIGH | To Do | OK
Write community rules + FAQ document | Community Setup | @big_quiv | Apr 12, 2026 | 10 | MEDIUM | To Do | OK
Create onboarding checklist for new students (pinned Notion doc) | Community Setup | @big_quiv | Apr 16, 2026 | 14 | MEDIUM | To Do | OK
Set up weekly check-in cadence in Telegram group | Community Setup | @big_quiv | Apr 19, 2026 | 17 | MEDIUM | To Do | OK
Create "before you start" resource document for each track | Community Setup | @big_quiv | Apr 22, 2026 | 20 | LOW | To Do | OK
Prepare and rehearse M1 live session for all 3 topics | Class Delivery | @big_quiv | Apr 28, 2026 | 26 | HIGH | To Do | ⚠ YES | RISK: First live session (Apr 28 or May 1) needs a full dry-run. Allocate 2 hrs for rehearsal on Day 26.
Test Google Meet screen share, audio, and recording | Class Delivery | @big_quiv | Apr 20, 2026 | 18 | HIGH | To Do | OK
Create session agenda template for all live classes | Class Delivery | @big_quiv | Apr 24, 2026 | 22 | MEDIUM | To Do | OK
Set up recording workflow: Google Meet → Drive → Notion link | Class Delivery | @big_quiv | Apr 22, 2026 | 20 | HIGH | To Do | OK
Prepare Q&A protocols: how to handle common questions live | Class Delivery | @big_quiv | Apr 26, 2026 | 24 | LOW | To Do | OK
Draft completion certificate and test PDF generation | Class Delivery | @big_quiv | Apr 30, 2026 | 28 | LOW | To Do | OK